Two-Week Action Plan

Foreign Investment section — Lisbon Housing Field Lab, Nova SBE — Sept 6–20, 2026

This covers your individual deliverable (§2.3, §3, §4.2.2, §5/6.3 — foreign investment) and what still needs to happen on the shared baseline. Built from the Field Lab brief, thesis_project_context.md, and a past Work Project from your program used as a structural example.

# 1. Where things stand — baseline model (shared)

| Item | Status | Note |
| --- | --- | --- |
| TWFE pipeline (7 specs) | HAVE | run_baseline.py, R² = 0.927, fully reproducible via setup.sh + one command |
| Merged data file | HAVE | district_quarter_full_dataset.csv — price, transactions, mortgage rate, FDI, unemployment, construction costs, population all in one table |
| Pipeline re-run on merged data | NEED | Old results still reflect the version without unemployment/construction costs/population. Quick to do — say the word. |
| Unit of analysis | PARTIAL | Spec calls for freguesia × quarter; what's built is district × quarter (freguesia data isn't available as a time series — see §5 below). Needs to be stated explicitly as a scoping decision in §3.4/§6.1, not left implicit. |
| Immigration inflow variable | NEED | Teammate's subtopic — confirm status with them this week |
| Infrastructure investment proxy | NEED | Teammate's subtopic |
| Supply-constraint proxy | NEED | Teammate's subtopic |

# 2. Where things stand — your part (foreign investment)

| Item | Status | Note |
| --- | --- | --- |
| FDI series (BdP) | HAVE | Transactions, stock, total — full history 2008–2026, quarterly, national |
| Golden Visa historical data | HAVE | 2012–2024, approvals/routes/investment/nationality, primary vs. secondary years flagged |
| Lisbon freguesia prices (INE, primary) | PARTIAL | Q1 2025 official INE release — 15 of 24 freguesias with exact €/m² figures, in the PDF already in your folder (16PreçosHabLocal_1T2025). One real snapshot, not a time series. |
| Lisbon freguesia prices (secondary) | PARTIAL | Q1 2026, all 24 freguesias, third-party compilation of INE data — cite as secondary |
| Foreign buyer price gap (tax residence) | PARTIAL | Same INE PDF: Grande Lisboa transactions by foreign vs. domestic tax residence buyers, with a real €/m² gap — this is the exact 'buyer by tax residence' variable your context doc flagged as unsourced. Only at Grande Lisboa/sub-region level, not freguesia. |
| Geographic unit for the causal model | NEED | Undecided: freguesia (data too thin for a real panel) vs. city-level comparison (Lisboa vs. Porto vs. 5 others, real quarterly data 2016–2021). Gates everything below — decide first. |
| Airbnb / tourism density | NEED | Source identified (Inside Airbnb, Lisbon) — not downloaded |
| Local-exposure (Bartik) construction | NEED | Converts the national FDI series into something that varies geographically — depends on the unit decision above |
| Heterogeneity covariates | NEED | Distance to center, foreign-population share, housing stock age — none sourced yet |
| Confidencial Imobiliário access | NEED | Richest freguesia-level data — pending advisor/NOVA IMS protocol, don't wait on it |
| DML + Causal Forest code | NEED | Not started — baseline TWFE is built, the causal model isn't |
| Literature review (§2.3) | NEED | Source list and target journals identified; no reading/writing done yet |
| The 25 pages | NEED | Not started |

# 3. What the guidelines actually require

From the Field Lab brief and the one full example Work Project available (a completed Nova SBE Business Analytics thesis, different topic, used here only for structure/format):

- Deliverables: final academic thesis report, replicable ML pipeline documentation, and (optional, worth including) a dashboard tab.

- Individual work: “Causal ML implementation (DML / Causal Forests)” is explicitly one of the four individual roles — that's your role, matched to your subtopic.

- Collective work: research design, data collection/cleaning, model integration, policy interpretation, final presentation — coordinate these with the group, don't duplicate effort.

- Advisor's role: methodological guidance on the causal ML, code review, feedback on drafts — use Prof. Matos for exactly this, not for data-hunting questions.

- Structure (from the example thesis): title page → abstract → keywords → contents → shared Introduction/Data/Baseline chapters → one substantial method section per student → shared Results chapter with one subsection per student → shared Discussion/Conclusion → references → appendix. Your §5/6.3 is that “one substantial section.”

- Citation style in the example: author–year, references alphabetical by surname (“Lastname, First, ‘Title,’ Journal, Year, vol(issue), pages”) — use this for consistency across the group document.

Not found in your files: an exact page count, margin/font spec, or submission deadline. The “25 pages” figure isn't in the Field Lab brief or the example thesis — it's presumably in Nova SBE's general Work Project formatting guidelines, a separate document from the program office. Worth a 2-minute check on the program portal before you format anything, so you're not reformatting later.

# 4. Sources — how to move fast without losing rigor

| For | Use | Notes |
| --- | --- | --- |
| Academic literature | Google Scholar (primary search) → RePEc/IDEAS → BdP Working Papers → RCAAP → Nova SBE library (EBSCO/ScienceDirect/JSTOR) | Target journals: Journal of Housing Economics, Journal of Urban Economics, Regional Science and Urban Economics. I can run this search and draft a first-pass literature synthesis for you to edit — faster than reading 20 papers cold. |
| Reference management | Zotero (free) | Matches the author–year style in the example thesis; browser plug-in saves a citation in one click while you search |
| Data already sourced | See tables above + prior deliverables this session | Don't re-search these — Golden Visa CSV, FDI series, freguesia snapshots, district panel are all done |
| Causal ML method background | econml / DoubleML documentation + the original Chernozhukov et al. (2018) DML paper and Wager & Athey (2018) causal forests paper | These two papers are close to mandatory citations for §4.2.2/§5 — read them first, everything else builds on them |

# 5. The one decision that unblocks everything

Freguesia-level Lisbon prices exist (confirmed — INE tracks all 24) but only as two disconnected snapshots (Q1 2025, Q1 2026), not a quarterly panel. A causal forest needs many time-varying observations to split on; two points can't support that. Two honest paths:

- City comparison (recommended given the timeline): Lisboa vs. Porto vs. 5 other cities, real quarterly data 2016–2021 already in hand. Use DiD / panel regression rather than a causal forest — more standard, matches the data you actually have, and is defensible to write up in the time left.

- Freguesia (higher risk): Use the two snapshots as a descriptive/motivating exhibit only (e.g. “prices diverged 12% between high- and low-FDI-exposure freguesias in one year”), not as the panel the causal model runs on. Only worth pursuing further if Confidencial Imobiliário access comes through soon — don't wait on it.

Decide this in the next 1–2 days — the Bartik instrument, the heterogeneity covariates, and the DML/Causal Forest code all depend on which unit you pick.

# 6. Day-by-day (Sept 6 – 20)

## Week 1 — decide, finish data, start literature

| Days | Task | Who |
| --- | --- | --- |
| Sun–Mon (7–8) | Decide geographic unit (§5). Check Nova SBE portal for formal page/format guidelines. | You |
| Mon (8) | Re-run baseline pipeline on the merged dataset; regenerate tables/figures/write-up | Me, on request |
| Tue–Wed (9–10) | Literature search + first-draft synthesis for §2.3 (foreign investment lit review) | Me first pass, you edit |
| Tue–Wed (9–10) | Download Airbnb data; extract remaining freguesia figures from the INE PDF you have (Porto too, if useful for city comparison) | You / me |
| Thu–Fri (11–12) | Build treatment variables: Golden Visa indicator (have it), foreign-buyer-share proxy, local-exposure/Bartik conversion of the FDI series | Me |
| Weekend (12–13) | Read Chernozhukov et al. (2018) and Wager & Athey (2018) — needed before writing §4.2.2/§5 | You |

## Week 2 — model, write, polish

| Days | Task | Who |
| --- | --- | --- |
| Mon–Tue (14–15) | Implement DML for the average treatment effect (econml or DoubleML) | Me + you reviewing |
| Wed (16) | Causal Forest for heterogeneous effects; generate figures | Me + you reviewing |
| Thu (17) | No-Golden-Visa counterfactual simulation | Me |
| Fri–Sat (18–19) | Write §2.3, §3 (your part), §4.2.2, §5/6.3 — draft from results + lit synthesis, you add interpretation/voice | Me draft, you rewrite in your voice |
| Sun (20) | Merge into shared group document, check formatting/citation consistency against the guidelines, send to Prof. Matos | You |

This is tight but doable if the unit decision happens now, not week 2. The literature review and the write-up are the two steps most likely to run long — hand me the drafting load on both and spend your own time on the parts that need your judgment: the geography decision, reading the two core methodology papers, and rewriting the draft into your own voice.